## Legend
Risk Score Equation |  |  |  |  | Impact
Risk Score = Likelihood x Impact |  |  |  |  | Scale | Rating | Description
[5 empty] | 3 | High | Significant financial loss ( Higher than $25-75K )
[5 empty] | 2 | Medium | Moderate financial loss ( Between $5k to $25K )
[5 empty] | 1 | Low | Less than $5K
Risk Score | Risk Level | Meaning |  |  | Likelihood
1 - 2 | Low | Acceptable |  |  | Scale | Rating | Description
3 - 5 | Medium | Needs mitigation or justification |  |  | 3 | Likely | High probability of occurrence within 12 months; historical precedent exists.
6 - 9 | High | Unacceptable, treatment required |  |  | 2 | Medium | Moderate chances of occurances. May Happen
[5 empty] | 1 | Unlikely | Unlikely to happen. Very rare occurrence.
Risk Identifier | Risk Description | Likelihood | Impact | Impact Description | Inherent Risk Score | Residual Risk | CIS v8 Mapping | Key Controls | Mitigation Notes | Risk Owner
R1 | Guest Wi-Fi being used to attack internal business systems. | 2 | 2 | Attackers could compromise the POS system or employee devices, thus leading to other risks. | 4 | 2 | CIS 12.1, 12.2 | VLANs, Separate guest and Business Networks, WPA3 | Use separate Wi-Fi networks for guests and employees. Ensure to use the latest encryption algorithm for wifi passwords, such as WPA3. | Devon, Founder and Lead Barista
R2 | Unauthorized access to security camera feeds. | 2 | 1 | Unauthorized access to security feeds could enable spying or stalking. | 2 | 1 | CIS 4.1 | Robust password policy, MFA | Use a strong, one-of-a-kind passphrase for IP cameras and use MFA if available. | Devon, Founder and Lead Barista
R3 | Breach of customer loyalty database. | 2 | 3 | Personal information, such as phone numbers and email addresses, could be leaked. | 6 | 3 | CIS 3.3, 6.1 | Encryption, Access Controls | Do not store more information than is needed on the customer loyalty platform. Encrypt the database at rest. Limit database access to only the employees and the application that need it. | Devon, Founder and Lead Barista
R4 | Phishing attack against employee email accounts. | 3 | 3 | Business passwords could be stolen, leading to confidential data leaks, extortion, and reputational damage. | 9 | 3 | CIS 6.3, 14.1 | MFA, Training | Train employees in phishing awareness. Ensure MFA is enabled. Use separate personal and business emails. | Tina, Founder and Chief of Adoptions
R5 | Theft of payment card information through compromised POS terminals. | 1 | 3 | Customers' card information could be stolen, leading to lawsuits, reputational damage, and fines. | 3 | 3 | CIS 1.1, 4.3 | Physical security, Patch Management | Ensure the business is properly locked at night so that unauthorized access cannot tamper with pos devices. Keep POS systems up to date. | Tina, Founder and Chief of Adoptions
R6 | Insider threat from a disgruntled employee. | 1 | 3 | A disgruntled employee could expose confidential customer or business data. | 3 | 2 | CIS 5.3, 6.2 | Access Controls | Ensure employees' access to confidential data is revoked before termination or departure. | Devon, Founder and Lead Barista
R7 | Social media account takeover damaging brand reputation. | 2 | 3 | An attacker could post brand- and reputation-damaging things on the company's social media account. | 6 | 3 | CIS 6.5 | MFA, User training | Limit access to the social media account. Use MFA for all social media accounts. Train social media admins about common scams. | Jake, Social media admin and marketer
R8 | Malware introduced through USB devices. | 1 | 2 | The malware could lead to a ransomware incident. See R13 for more details on ransomware incidents. | 2 | 2 | CIS 10.3 | User Training | Train employees about USB attacks. | Devon, Founder and Lead Barista
R9 | Distributed Denial of Service (DDoS) attack on the online booking website. | 2 | 2 | The booking site being down would interfere with day-to-day business operations. Customers could not schedule appointments. | 4 | 2 | CIS 9.5 | Business Continuity Planning. | Have alternative ways to make reservations, such as social media, in case that happens. | Jake, Social media admin and marketer
R10 | Third-Party booking site data breach | 1 | 2 | Personal Customer information would be leaked, leading to reputational damage and potential lawsuits. | 2 | 2 | CIS 15.1, 15.2 | Third Party Risk Assessments and Audits | Conduct a 3rd party risk assessment to understand the risks of a certain booking service. | Tina, Founder and Chief of Adoptions
R11 | Adoption Record leakage | 2 | 3 | Government IDs of customers could be leaked, leading to fines or lawsuits and loss of brand reputation. | 6 | 2 | CIS 3.1, 3.8 | Access Controls, Encryption, | Ensure adoption records are encrypted at rest. Ensure strict access controls for adoption records. | Tina, Founder and Chief of Adoptions
R12 | Third-party employment payroll system outage | 1 | 2 | Employees would be without pay for the duration of the system outage. | 2 | 2 | CIS 11.1 | Business continuity planning | Have alternative ways to pay employees during a long outage, such as checks or money-sending apps. | Angela, CFO
R13 | A ransomware attack that infects the business devices and makes operations impossible | 2 | 3 | This would devastate the business, potentially destroy records, and leave business assets unusable. | 6 | 2 | CIS 10.1, 11.2 | EDR, Patch Management, Back-Ups, Disaster Recovery, Secure Data storage | Ensure Windows Defender is enabled and apply the latest patches when available. Back up systems regularly and test backups to ensure they work when needed. Store non-day-to-day PII and confidential information on a separate storage media that is offline and encrypted at rest. | Devon, Founder and Lead Barista